tiny-os

Implementation Phases

Rust · Raspberry Pi 5 (BCM2712) · AArch64

Portable to other ARM Cortex-A / Cortex-M cores

March 2026 · Version 1.0

# Table of Contents

# Overview

This document breaks the implementation of tiny-os into ten incremental phases. Each phase produces a working, testable system that builds on the previous phase. The design prioritizes portability: every phase identifies which components are architecture-specific and wraps them behind Rust traits so that porting to a new ARM core (or beyond) requires implementing a bounded set of trait impls rather than rewriting the entire phase.

The primary target is the Raspberry Pi 5 (BCM2712 SoC, quad Cortex-A76, GIC-400, RP1 southbridge). The architecture assumes bare-metal operation with the RPi firmware loading the kernel image and passing a device tree blob.

## Phase Dependency Map

Each phase depends on the ones before it. Phases 8–10 have some internal parallelism — DMA and block storage can proceed alongside the filesystem if the block device trait is defined early.

| # | Phase | Depends On | Duration | Core / Portable |
| --- | --- | --- | --- | --- |
| 1 | Bare-Metal Bootstrap & UART Console | — | 2–3 weeks | Mostly arch |
| 2 | Exception Vectors, GIC-400 & Timer IRQ | Phases 1–1 | 2–3 weeks | Mostly arch |
| 3 | Memory Management — Page Allocator & MMU | Phases 1–2 | 3–4 weeks | Mostly arch |
| 4 | Task Model & Preemptive Scheduler | Phases 1–3 | 3–4 weeks | Mixed |
| 5 | Synchronization Primitives & IPC | Phases 1–4 | 2–3 weeks | Mixed |
| 6 | Device Driver Framework & Core Drivers | Phases 1–5 | 3–4 weeks | Mixed |
| 7 | SMP — Multi-Core Scheduling | Phases 1–6 | 3–4 weeks | Mixed |
| 8 | DMA Engine & Block Storage | Phases 1–7 | 3–4 weeks | Mostly portable |
| 9 | Filesystem & Shell | Phases 1–8 | 3–4 weeks | Mostly portable |
| 10 | Networking (Ethernet/WiFi) & User-Space Foundation | Phases 1–9 | 4–6 weeks | Mostly arch |

## Estimated Timeline

Total estimated effort: 28–40 weeks for a single developer working part-time, or 14–20 weeks full-time. Phases 1–5 form the "minimum viable RTOS" (~12–17 weeks) — a preemptive multi-tasking kernel with synchronization, suitable for embedded use without a filesystem or networking.

# Phase 1: Bare-Metal Bootstrap & UART Console

"First light" — prove the toolchain works and get serial output

Estimated duration: 2–3 weeks

## Goal

Boot the BCM2712 in AArch64 EL1, initialize UART via RP1, print to a serial console. This is the foundation everything else builds on.

## Deliverables

- Cargo workspace with a no_std, no_main binary crate (kernel) and a shared crate (arch) for platform abstractions.

- Linker script placing kernel at 0x80000 (RPi firmware load address), defining .text, .rodata, .data, .bss, and stack sections.

- Assembly entry point (_start) in AArch64: parks secondary cores in WFE loops, zeroes .bss, sets SP, branches to a Rust kmain().

- Minimal RP1 UART driver (UART0 at the RP1 peripheral window 0x1F_0000_0000 + offset) using MMIO volatile writes. Leverages uart_early_init=1 in config.txt so firmware pre-initializes the PCIe link and UART baud rate.

- A kprint!() / kprintln!() macro backed by core::fmt::Write for formatted output.

- panic_handler that prints the panic message and location, then enters an infinite WFE loop.

- Build pipeline: cargo + aarch64-none-elf target, objcopy to produce kernel8.img, deploy to SD card.

## Portability Considerations

Isolate all BCM2712/RP1 specifics behind a UartDriver trait and a board module. Future ports supply their own implementation (e.g., PL011 for QEMU virt, or USART for STM32).

## Verification & Testing

Manual: boot on real hardware or QEMU -M raspi4b (closest available), confirm "tiny-os booting…" on serial. Automated: host-side unit tests for kprint formatting logic.

## Risks & Mitigations

- RP1 PCIe link not preserved — mitigated by pciex4_reset=0 and uart_early_init=1.

- QEMU does not yet model BCM2712 — use raspi4b machine or run on real hardware.

# Phase 2: Exception Vectors, GIC-400 & Timer IRQ

"The kernel can respond to interrupts"

Estimated duration: 2–3 weeks

## Goal

Install EL1 exception vectors, bring up the GIC-400 interrupt controller, and route the ARM Generic Timer to produce a periodic tick — the heartbeat for the future scheduler.

## Deliverables

- Exception vector table (VBAR_EL1) with 16 entries aligned to 2 KB. Dispatches Synchronous, IRQ, FIQ, and SError to Rust handlers. Saves/restores all general-purpose registers + SPSR_EL1/ELR_EL1 in a TrapFrame struct.

- GIC-400 distributor + CPU interface driver: enable distributor, set priority mask, configure individual interrupt IDs (SPIs for timer, UART RX, RP1 MSIs later).

- ARM Generic Timer driver: configure CNTP_CTL_EL0 / CNTP_TVAL_EL0 to fire at a configurable tick rate (default 1 kHz). The IRQ handler acknowledges the GIC, reloads the timer, and increments a global tick counter.

- A monotonic clock API: os_tick_count() → u64, os_uptime_ms() → u64.

- Early kernel shell over UART: a trivial command loop ("help", "uptime", "reboot") to exercise both UART RX interrupts and the tick counter interactively.

## Portability Considerations

Abstract behind an InterruptController trait (init, enable, disable, acknowledge, set_priority) and a Timer trait (init, set_period, acknowledge). The GIC-400 is common across Cortex-A53/A72/A76, so a single implementation covers many SoCs. Cortex-M ports would swap in NVIC + SysTick.

## Verification & Testing

Assert tick counter advances. Shell "uptime" matches wall-clock time ±5%. Verify a deliberately triggered Synchronous exception (SVC) is caught and reported rather than hanging.

## Risks & Mitigations

- GIC register offsets differ between GIC-400 and GICv3 — the BCM2712 uses GIC-400; abstract enough to swap later.

- Timer frequency depends on CNTFRQ_EL0 — read it at init rather than hard-coding.

# Phase 3: Memory Management — Page Allocator & MMU

"Virtual memory and safe allocation"

Estimated duration: 3–4 weeks

## Goal

Bring up the AArch64 MMU with identity-mapped kernel pages and a physical page frame allocator, so the kernel operates in a controlled virtual address space.

## Deliverables

- Physical memory map discovery: parse the DTB (device tree blob) passed by the RPi firmware at boot to find DRAM regions. Fallback: hard-coded map for known board revisions (1/2/4/8/16 GB).

- Bitmap page frame allocator: manages 4 KB pages, backed by a static array in .bss. Provides alloc_page() → PhysAddr and free_page(PhysAddr). O(1) via free-list head or CLZ bitmap scan.

- AArch64 MMU initialization: build a 4-level (or 3-level with 2 MB blocks) translation table. Identity-map the kernel image (RX for .text, RO for .rodata, RW for .data/.bss/.stack). Device-map MMIO regions (GIC, RP1 peripheral window) with nGnRnE attributes.

- A simple kernel heap: bump allocator or linked-list allocator implementing GlobalAlloc, enabling alloc::Box, alloc::Vec, etc. in the kernel.

- Guard pages at stack boundaries (unmapped pages that trigger a Data Abort on overflow).

- Memory protection attributes: kernel pages marked PXN where appropriate; device pages marked as non-cacheable, non-executable.

## Portability Considerations

PageAllocator and AddressSpace traits. The MMU setup is inherently architecture-specific (translation table format, TCR_EL1, MAIR_EL1, SCTLR_EL1 bits), so wrap it in an arch::mmu module. Other ARM cores share the same AArch64 translation format but may differ in cache policies and shareability domains.

## Verification & Testing

Allocate and free 1000 pages — verify no leaks (free count returns to original). Access a guard page — verify Data Abort is caught. Toggle a mapping to read-only — verify write fault fires. Run on both real hardware and QEMU.

## Risks & Mitigations

- Translation table alignment requirements are strict (4 KB-aligned pages for each table level) — enforce with #[repr(align(4096))].

- Cache coherency issues if MMU is enabled before caches are cleaned — follow the ARM Architecture Reference Manual enable sequence precisely.

# Phase 4: Task Model & Preemptive Scheduler

"Multi-tasking with real-time priorities"

Estimated duration: 3–4 weeks

## Goal

Implement the tiny-os task model and the fixed-priority preemptive scheduler from the scheduler specification. Multiple tasks timeshare the CPU with deterministic dispatch.

## Deliverables

- Task Control Block (TCB): task ID, priority (0–255), state (Ready/Running/Blocked/Suspended/Dormant), saved CPU context (all GP registers, SP, PC, SPSR, TPIDR_EL0), stack pointer, stack base/size, timing stats.

- Task creation API: os_task_create(entry_fn, priority, stack_size, name) → TaskId. Each task gets its own kernel stack allocated from the page allocator.

- Context switch routine in assembly: saves current task's registers to its TCB, loads the next task's registers, issues ISB, returns via ERET. Measured and validated for deterministic latency.

- 256-level priority bitmap scheduler: one bit per priority level, CLZ to find highest-priority ready task in O(1). Round-robin among equal-priority tasks via per-level FIFO queues.

- Preemption on every timer tick: the tick ISR invokes the scheduler; if a higher-priority task is now ready, a context switch occurs before returning from the IRQ.

- Idle task: lowest-priority task that executes WFI, yielding until the next interrupt.

- os_task_yield(), os_task_suspend(TaskId), os_task_resume(TaskId), os_task_sleep(ticks) APIs.

- Critical sections: os_enter_critical() / os_exit_critical() using DAIF masking with nesting count.

## Portability Considerations

The TCB and scheduler are architecture-agnostic (pure Rust). Only the context switch and critical-section primitives live in arch::context. Define a Context trait with save() / restore() / switch_to() so each architecture provides its own assembly stub.

## Verification & Testing

Spawn three tasks at different priorities — verify execution order. Suspend/resume a task — verify it stops/restarts. Measure context switch time with the cycle counter (PMCCNTR_EL0) — assert < 1 µs on BCM2712. Stress-test with 32 tasks for 10 million ticks — no hangs or stack corruption.

## Risks & Mitigations

- Stack overflow in tasks — mitigated by guard pages from Phase 3.

- Priority inversion — addressed in Phase 5.

# Phase 5: Synchronization Primitives & IPC

"Safe concurrency between tasks"

Estimated duration: 2–3 weeks

## Goal

Provide mutexes, semaphores, message queues, and event flags so tasks can synchronize and communicate safely, with priority inversion protection.

## Deliverables

- Binary and counting semaphores: os_sem_create(initial_count, max_count), os_sem_wait(timeout), os_sem_signal(). Wait queue ordered by priority.

- Mutex with Priority Inheritance Protocol (PIP): when a high-priority task blocks on a mutex held by a low-priority task, the holder's effective priority is temporarily boosted. Configurable per-mutex to use PIP or Priority Ceiling Protocol (PCP).

- Message queues: os_mq_create(msg_size, capacity), os_mq_send(msg, timeout), os_mq_recv(buf, timeout). Fixed-size messages in a ring buffer. Send/receive can block with timeout.

- Event flag groups: os_event_set(flags), os_event_wait(flags, AND|OR, timeout). Tasks block until a combination of flags is set.

- Timeout support on all blocking primitives: OS_WAIT_FOREVER, OS_NO_WAIT, or tick count. Timed-out waits return Err(Timeout).

- Deadlock detection (optional/debug mode): cycle detection in the wait-for graph, logged via kprintln!().

## Portability Considerations

All synchronization code is architecture-agnostic (uses critical sections from Phase 4). The only arch dependency is the atomic instruction set (LDXR/STXR on AArch64), wrapped in an arch::atomic module.

## Verification & Testing

Classic producer/consumer with message queue — verify no lost messages. Priority inversion test: low-priority task holds mutex, high-priority task blocks, medium-priority task does not run ahead of the boosted low-priority task. Timeout test: wait with 100-tick timeout returns Err after ~100 ms.

## Risks & Mitigations

- PIP with nested mutex acquisition — implement recursive priority tracking.

- Message queue memory — allocate from the kernel heap; consider static allocation for safety-critical configs.

# Phase 6: Device Driver Framework & Core Drivers

"Talking to hardware beyond UART"

Estimated duration: 3–4 weeks

## Goal

Establish a lightweight driver registration model and implement drivers for essential peripherals: GPIO, SPI, I²C, and a kernel logging subsystem.

## Deliverables

- Driver trait hierarchy: a base Driver trait (init, probe, name, status) with specialized sub-traits (GpioDriver, SpiDriver, I2cDriver, BlockDriver). Drivers register at boot via a static driver table.

- RP1 GPIO driver: 28 GPIO pins accessible through the RP1 peripheral window. Pin configuration (input, output, alt functions), pull-up/pull-down, interrupt on edge/level.

- RP1 I²C driver: master mode, configurable clock speed (100/400 kHz), blocking and interrupt-driven transfers. Useful for sensors, RTCs, EEPROMs.

- RP1 SPI driver: master mode, configurable clock, chip-select management, DMA-ready interface (DMA itself is Phase 8).

- Kernel logging subsystem (klog): severity levels (Error, Warn, Info, Debug, Trace), compile-time and runtime filtering, ring buffer for deferred output, timestamps from the monotonic clock.

- Device tree parsing (minimal): extract peripheral addresses and interrupt numbers from the DTB so drivers don't hard-code addresses.

## Portability Considerations

All drivers implement hardware-agnostic traits. Board support packages (BSPs) wire specific drivers to the trait interfaces. A new port implements a BSP module that maps its peripherals to the driver traits. The device tree parser is architecture-independent.

## Verification & Testing

GPIO loopback: set output pin high, read on connected input pin. I²C: scan bus, detect known device at expected address. SPI: loopback MOSI→MISO. klog: verify ring buffer wraps correctly and no messages lost under high throughput.

## Risks & Mitigations

- RP1 peripheral register documentation is limited — rely on the Linux kernel's RP1 driver source as reference.

- Bus contention if Linux is also running — tiny-os is bare-metal, so this is not an issue, but document for dual-OS scenarios.

# Phase 7: SMP — Multi-Core Scheduling

"Wake the other three Cortex-A76 cores"

Estimated duration: 3–4 weeks

## Goal

Bring secondary cores online and extend the scheduler to distribute tasks across all four Cortex-A76 cores with per-core run queues and cross-core migration.

## Deliverables

- Secondary core startup: release cores 1–3 from their WFE loops via PSCI (Power State Coordination Interface) or the spin-table method used by the RPi firmware. Each core initializes its own exception vectors, GIC CPU interface, and timer.

- Per-core run queues: each core has its own priority bitmap and ready queues. The scheduler runs independently on each core, picking from its local queue.

- Task affinity: os_task_set_affinity(TaskId, core_mask). Tasks can be pinned to a specific core or allowed to migrate.

- Load balancer: a periodic routine (running every N ticks) checks per-core load and migrates ready tasks from overloaded to underloaded cores. Migration respects affinity masks and requires cross-core IPIs (Inter-Processor Interrupts via GIC SGIs).

- SMP-safe synchronization: upgrade critical sections from DAIF masking to spin-locks (ticket locks or MCS locks) for cross-core mutual exclusion. Existing mutexes and semaphores gain spin-lock-guarded wait queues.

- Per-core idle tasks and per-core tick counters.

- os_smp_core_count() → usize, os_smp_current_core() → CoreId APIs.

## Portability Considerations

Core startup is highly platform-specific (PSCI vs. spin-table vs. direct register poke). Abstract behind an SmpBoot trait. Spin-locks and IPIs are architecture-specific (WFE/SEV on ARM, PAUSE on x86). The load balancer and per-core queue logic are portable Rust.

## Verification & Testing

Boot all 4 cores — verify each prints its core ID. Run 8 tasks across 4 cores — verify parallel execution (wall-clock time < serial time). Pin a task to core 2 — verify it never runs on another core. Stress test: 32 tasks, random sleeps, run for 10M ticks — no deadlocks or corruption.

## Risks & Mitigations

- Cache coherency between cores — the BCM2712 Cortex-A76 cluster is fully coherent, but verify with memory barriers at context switch boundaries.

- Thundering herd on cross-core wakeups — use targeted SGIs rather than broadcast.

# Phase 8: DMA Engine & Block Storage

"High-throughput data movement and persistent storage"

Estimated duration: 3–4 weeks

## Goal

Implement DMA for zero-copy peripheral transfers and bring up SD/MMC and (optionally) NVMe block device access for persistent storage.

## Deliverables

- DMA controller driver: the BCM2712 DMA engine with scatter-gather support. Provides dma_transfer(src, dst, len, callback) with completion via interrupt. Allocate DMA-safe buffers from a non-cacheable memory pool.

- SD/MMC host controller driver (EMMC2): initialize the SD card, send CMD0/CMD8/ACMD41/CMD2/CMD3 initialization sequence, read/write 512-byte sectors. Supports both polling and DMA modes.

- Block device abstraction: a BlockDevice trait with read_blocks(lba, count, buf) and write_blocks(lba, count, buf). The SD driver implements this trait.

- Optional NVMe driver stub: if targeting the Pi 500/CM5 with M.2, a minimal NVMe driver over PCIe (Phase 10 dependency). Can be deferred.

- DMA-aware SPI and I²C: upgrade Phase 6 drivers to use DMA for large transfers, falling back to PIO for small ones.

- Simple partition table parser: read MBR or GPT to locate partitions.

## Portability Considerations

BlockDevice trait is fully portable. DMA engines vary wildly across SoCs — wrap in a DmaEngine trait with platform-specific implementations. SD/MMC protocol is standard but host controller registers differ; split into protocol logic (portable) and host driver (platform-specific).

## Verification & Testing

DMA memcpy: copy 1 MB, verify contents match. SD: read sector 0 (MBR), verify 0x55AA signature. Write a test sector, read it back, compare. Throughput benchmark: sequential read MB/s should approach hardware limits.

## Risks & Mitigations

- SD card initialization is notoriously finicky — implement robust retry and timeout logic.

- DMA buffer alignment requirements — enforce at the allocator level.

# Phase 9: Filesystem & Shell

"Read files, run scripts, log to disk"

Estimated duration: 3–4 weeks

## Goal

Implement a FAT32 filesystem (for SD card compatibility) and a richer interactive shell with command history, scripting, and persistent logging.

## Deliverables

- FAT32 filesystem driver: mount, open, read, write, seek, close, mkdir, readdir, stat, unlink. Handles long filenames (LFN). Operates on top of the BlockDevice trait from Phase 8.

- Virtual Filesystem (VFS) layer: a unified namespace that can mount multiple filesystems. Provides open/read/write/close with file descriptors. Initial backends: FAT32, and a devfs for /dev/uart0, /dev/null, /dev/random.

- Enhanced shell: command history (up/down arrows via ANSI escape parsing), tab completion for filenames, I/O redirection (> and <), built-in commands: ls, cat, hexdump, cp, rm, mkdir, mount, umount, free, ps, top, reboot, log.

- Persistent kernel log: klog writes to /var/log/kernel.log on the FAT32 partition, with rotation when the file exceeds a configurable size.

- Boot-time script: if /etc/init.sh exists, the shell executes it line-by-line at startup for automated configuration.

## Portability Considerations

The VFS and shell are entirely platform-agnostic. FAT32 is platform-agnostic (operates on BlockDevice). Only the underlying block driver is platform-specific.

## Verification & Testing

Create a file, write known data, unmount, remount, read back — verify integrity. Fill the filesystem to capacity — verify graceful error. Shell: run a scripted test via init.sh that creates files and checks output. FAT32 interop: mount the SD card on a Linux host and verify files created by tiny-os are readable.

## Risks & Mitigations

- FAT32 corruption on power loss — implement write ordering discipline (metadata after data) and consider a journal or WAL for critical writes.

- Long filename support adds complexity — consider starting with 8.3 filenames and adding LFN as an enhancement.

# Phase 10: Networking (Ethernet/WiFi) & User-Space Foundation

"Connect to the outside world and prepare for user tasks"

Estimated duration: 4–6 weeks

## Goal

Bring up networking (Ethernet via RP1's MAC, optionally WiFi) with a TCP/IP stack, and lay the groundwork for memory-isolated user-space tasks using EL0.

## Deliverables

- RP1 Ethernet MAC driver: initialize the RP1's gigabit Ethernet controller, link detection, DMA-based packet TX/RX. Implements a NetDevice trait.

- Lightweight TCP/IP stack: either a from-scratch minimal stack or integrate smoltcp (a Rust no_std TCP/IP library). Supports ARP, IPv4, ICMP (ping), UDP, TCP, and DHCP client.

- Socket API: os_socket_create(), os_socket_bind(), os_socket_listen(), os_socket_accept(), os_socket_connect(), os_socket_send(), os_socket_recv(). Blocking with timeout.

- Telnet server: remote shell access over TCP — connects to the Phase 9 shell.

- User-space task support (EL0): tasks run in EL0 with their own virtual address space (isolated page tables). System calls via SVC trap to EL1. Initial syscalls: write, read, exit, yield, sleep, getpid.

- ELF loader: load a statically linked AArch64 ELF binary from the filesystem into a user-space address space and begin execution.

- MPU/MMU isolation: user tasks cannot access kernel memory or other tasks' memory. Faults in user tasks are caught and the task is killed, not the whole system.

## Portability Considerations

smoltcp is already portable Rust. The NetDevice trait abstracts the NIC. User-space isolation requires architecture-specific page table and exception level management (EL0/EL1 on ARM, Ring 3/0 on x86). Define a UserContext trait for each architecture.

## Verification & Testing

Ping test: assign IP via DHCP, ping from a host — verify replies. TCP echo server: connect from host, send data, verify echo. User-space: load a "hello world" ELF, verify it prints via syscall and exits cleanly. Fault isolation: user task dereferences NULL — verify it is killed without kernel panic.

## Risks & Mitigations

- RP1 Ethernet MAC documentation is sparse — use Linux kernel driver as reference.

- TCP/IP stack complexity — smoltcp is well-tested and avoids reinventing the wheel.

- User-space adds significant complexity to the memory management and exception handling — expect this to be the longest phase.

# Appendix A: Portability Trait Summary

The following table summarizes the key Rust traits that form the Hardware Abstraction Layer (HAL). A port to a new ARM core or board requires implementing these traits — the rest of the kernel, scheduler, synchronization, filesystem, and networking code compiles unchanged.

| Trait | Introduced | Module | Key Methods |
| --- | --- | --- | --- |
| UartDriver | Phase 1 | arch::uart | init(), write_byte(), read_byte(), write_str() |
| InterruptController | Phase 2 | arch::irq | init(), enable(id), disable(id), acknowledge() → IrqId, set_priority(id, pri) |
| Timer | Phase 2 | arch::timer | init(freq), set_period(ticks), acknowledge(), read_counter() → u64 |
| PageAllocator | Phase 3 | mm::alloc | alloc_page() → PhysAddr, free_page(PhysAddr), available() → usize |
| AddressSpace | Phase 3 | arch::mmu | new(), map(virt, phys, flags), unmap(virt), activate() |
| Context | Phase 4 | arch::context | new(entry, stack_top) → Self, switch_to(&mut self, &Self) |
| SmpBoot | Phase 7 | arch::smp | core_count() → usize, start_core(id, entry) → Result, current_core() → CoreId |
| DmaEngine | Phase 8 | arch::dma | transfer(src, dst, len, cb) → DmaHandle, abort(handle) |
| BlockDevice | Phase 8 | drivers::block | read_blocks(lba, count, buf), write_blocks(lba, count, buf), block_size() → usize |
| NetDevice | Phase 10 | drivers::net | init(), send(packet), recv() → Option<Packet>, mac_address() → [u8;6] |
| UserContext | Phase 10 | arch::user | new(elf_entry, user_stack) → Self, enter(), handle_syscall(trap_frame) |

# Appendix B: Suggested Cargo Workspace Layout

The workspace separates architecture-specific code from portable kernel logic, making it straightforward to add new port targets.

tiny-os/

├── Cargo.toml                  # Workspace root

├── kernel/                     # Main kernel binary

│   ├── Cargo.toml

│   ├── src/

│   │   ├── main.rs             # kmain() entry point

│   │   ├── sched/              # Scheduler, task model

│   │   ├── sync/               # Mutex, semaphore, MQ, events

│   │   ├── mm/                 # Page allocator, heap, VMM

│   │   ├── fs/                 # VFS, FAT32

│   │   ├── net/                # TCP/IP, sockets

│   │   ├── drivers/            # Driver traits + registry

│   │   ├── shell/              # Interactive shell

│   │   └── klog/               # Kernel logging

│   └── link.ld                 # Linker script (per-target)

├── arch/                       # Architecture crate

│   ├── Cargo.toml

│   └── src/

│       ├── lib.rs

│       ├── aarch64/            # AArch64-specific

│       │   ├── boot.S          # _start, vector table

│       │   ├── context.rs      # Context switch

│       │   ├── mmu.rs          # Translation tables

│       │   ├── gic.rs          # GIC-400 driver

│       │   ├── timer.rs        # Generic Timer

│       │   └── smp.rs          # Multi-core startup

│       └── cortex_m/           # Future: Cortex-M port

├── bsp/                        # Board Support Packages

│   ├── Cargo.toml

│   └── src/

│       ├── rpi5/               # Raspberry Pi 5

│       │   ├── mod.rs

│       │   ├── rp1_uart.rs

│       │   ├── rp1_gpio.rs

│       │   ├── rp1_eth.rs

│       │   ├── emmc2.rs

│       │   └── memory_map.rs

│       └── qemu_virt/          # QEMU virt machine

└── tools/                      # Host-side utilities

├── mkimg.sh                # Build kernel8.img

└── deploy.sh               # Flash to SD card